## Gantt Chart
ACTIVITY | JULY 2026
| W1 (14-17 Jul) |  |  |  | W1 | W2 (21-27 Jul)
| 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27
SPRINT 1 - Auto Approval PO < USD 500
Build & Push Program ZPO_AUTO_RELEASE (v4)
Setup Mapping ZMAP_TYPE (Threshold & Approver)
Validasi Business Rule (Threshold & Release Strategy)
Siapkan Data Test PO <= USD 500
Jadwalkan Background Job (SM36)
Testing End-to-End Tier T0
Bugfix (jika ada)
UAT & Sign-off Tier T0
Siapkan Transport Request (SE09/SE10)
Release ke QAS & Dokumentasi Teknis
Closing / Demo Sprint 1
SPRINT 2 - Approval Flow & Email Notification
Finalisasi Requirement Approval Flow
Design CONFIG Switch & Kerangka Notifikasi
Build Logic Kirim Email (SO_NEW_DOCUMENT_ATT_SEND_API1)
Siapkan Template Email & Finalisasi Approver
Unit Test Pengiriman Email
Review Isi & Format Email
Testing End-to-End Tier T1/T2
Aktifkan Switch NOTIF_ACTIVE
UAT & Sign-off Sprint 2
Transport ke QAS & Handover
Legend:
Done
In Progress
Planned / Not Started

## PO Auto Release
Daily Activity - PO Auto Release Automation
SPRINT 1 - Auto Approval PO < USD 500 - 14 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-01 Build & push program ZPO_AUTO_RELEASE (v4) - auto-release Tier T0 <USD 500 via BAPI_PO_RELEASE | Program ZPO_AUTO_RELEASE aktif di sandbox-new (TRS) | Program ZPO_AUTO_RELEASE ter-deploy | Done | 100% | 2026-07-14
Budi (ABAP) | SPR1-02 Setup mapping ZMAP_TYPE (THRESHOLD T0/T1/T2 & APPROVER nama+email per EKGRP) | Mapping threshold & approver siap dipakai program | ZMAP_TYPE terisi & tervalidasi | Done | 100% | 2026-07-14
Alfa (Functional) | SPR1-03 Review & validasi business rule threshold USD 500 dan release strategy (FRGGR/FRGSX) sesuai Customizing | Konfirmasi threshold & release group sudah sesuai proses bisnis | Sign-off business rule Tier T0 | In Progress | 25% | 2026-07-17
SPRINT 1 - Auto Approval PO < USD 500 - 15 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR1-04 Siapkan/koordinasi data PO test senilai <= USD 500 di sandbox utk validasi end-to-end Tier T0 | Ada PO test valid utk skenario auto-release | PO test tersedia | Not Started | 0% | 2026-07-16
Budi (ABAP) | SPR1-05 Jadwalkan background job (SM36) utk ZPO_AUTO_RELEASE berjalan periodik | Job berjalan otomatis tanpa perlu F8 manual | Job SM36 aktif | Not Started | 0% | 2026-07-16
SPRINT 1 - Auto Approval PO < USD 500 - 16 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi, Alfa | SPR1-06 Jalankan test end-to-end Tier T0 pakai PO test, verifikasi BAPI_PO_RELEASE tereksekusi & PO ter-release otomatis | Bukti empiris Tier T0 berhasil release | Hasil test terdokumentasi | Not Started | 0% | 2026-07-17
Budi (ABAP) | SPR1-07 Perbaikan bug (jika ada) dari hasil testing | Program bebas bug blocking | Bugfix (jika ada) | Not Started | 0% | 2026-07-17
SPRINT 1 - Auto Approval PO < USD 500 - 17 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR1-08 UAT bersama user/procurement, sign-off jalur Tier T0 | User setuju hasil auto-release Tier T0 | Berita acara UAT / sign-off | Not Started | 0% | 2026-07-17
Budi (ABAP) | SPR1-09 Siapkan transport request (SE09/SE10), pindah program dari $TMP ke package transportable | Program siap ditransport ke QAS | Transport request dibuat | Not Started | 0% | 2026-07-20
SPRINT 1 - Auto Approval PO < USD 500 - 20 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-10 Release transport ke QAS (STMS) & dokumentasi teknis program | Program live di QAS | Dokumentasi teknis (technical spec) | Not Started | 0% | 2026-07-20
Alfa (Functional) | SPR1-11 Dokumentasi business rule & closing/demo Sprint 1 ke stakeholder (Douglas Tjokro/William) | Sprint 1 resmi ditutup & didemokan | Dokumen closing Sprint 1 | Not Started | 0% | 2026-07-20
SPRINT 2 - Approval Flow & Email Notification (asumsi 1 minggu, samakan dgn Sprint 1) - 21 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-01 Finalisasi requirement approval flow (email notifikasi biasa vs approve-via-link) bersama business | Scope Sprint 2 disepakati | Dokumen requirement final | Not Started | 0% | 2026-07-21
Budi (ABAP) | SPR2-02 Design CONFIG switch ZMAP_TYPE (TYPE=CONFIG, OPT=NOTIF_ACTIVE) & kerangka FORM notifikasi (dormant) | Switch siap, kode belum aktif | Kerangka kode notifikasi | Not Started | 0% | 2026-07-22
SPRINT 2 - Approval Flow & Email Notification - 22 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-03 Build logic kirim email (FM SO_NEW_DOCUMENT_ATT_SEND_API1) ke appr_mail utk status='M' | Email terkirim ke approver sesuai EKGRP | Fungsi kirim email | Not Started | 0% | 2026-07-23
Alfa (Functional) | SPR2-04 Siapkan template isi email (subject/body) & finalisasi daftar approver (Lisa/Melisa/Fenny) | Template & mapping approver final | Template email disetujui | Not Started | 0% | 2026-07-22
SPRINT 2 - Approval Flow & Email Notification - 23 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-05 Unit test pengiriman email dari ZPO_AUTO_RELEASE (mode simulasi P_TEST=X) | Email test terkirim sesuai approver mapping | Hasil unit test | Not Started | 0% | 2026-07-23
Alfa (Functional) | SPR2-06 Review isi & format email hasil test | Email sesuai standar komunikasi perusahaan | Approval isi email | Not Started | 0% | 2026-07-24
SPRINT 2 - Approval Flow & Email Notification - 24 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi, Alfa | SPR2-07 End-to-end testing Tier T1/T2: approver terima email -> approve manual di ME29N -> validasi status | Alur notifikasi & approval manual terverifikasi | Hasil test E2E | Not Started | 0% | 2026-07-24
Budi (ABAP) | SPR2-08 Aktifkan switch NOTIF_ACTIVE='X' di sandbox setelah testing OK | Notifikasi email aktif di sandbox | Switch aktif | Not Started | 0% | 2026-07-24
SPRINT 2 - Approval Flow & Email Notification - 27 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-09 UAT & sign-off Sprint 2 bersama user/procurement | User setuju alur notifikasi & approval | Berita acara UAT Sprint 2 | Not Started | 0% | 2026-07-27
Budi (ABAP) | SPR2-10 Transport Sprint 2 ke QAS, dokumentasi final & handover | Sprint 2 live di QAS, project selesai | Dokumentasi final & handover | Not Started | 0% | 2026-07-27

## Catatan Asumsi
Catatan asumsi timeframe:
1. Format tabel mengikuti template 'ABAP' pada file (USER) WBS & Daily Activity-COA Automation.xlsx yang di-upload Baginda.
2. Sprint 1 mulai 14 Juli 2026 (hari ini), durasi 1 minggu kerja (5 hari kerja: 14, 15, 16, 17, 20 Juli 2026 - melompati Sabtu/Minggu 18-19 Juli).
3. Sprint 2 diasumsikan durasi sama (1 minggu kerja: 21, 22, 23, 24, 27 Juli 2026) karena durasi Sprint 2 belum dikonfirmasi eksplisit oleh Baginda. Mohon dikoreksi jika berbeda.
4. Tim: Budi (ABAP Developer), Alfa (Functional Consultant).
5. Status & Status (%) untuk seluruh task Sprint 1 hari ke-2 s.d. Sprint 2 masih 'Not Started' / 0% karena timeframe ini dibuat di awal Sprint 1 (hari pertama) - silakan update seiring progres berjalan.
6. Dua task hari pertama Sprint 1 (SPR1-01, SPR1-02) ditandai 'Done' 100% karena program ZPO_AUTO_RELEASE v4 dan mapping ZMAP_TYPE sudah selesai dibangun & di-push ke sandbox-new pada percakapan sebelumnya.