## Gantt Chart
ACTIVITY | JULI - AGUSTUS 2026
| SPRINT 1 (14-23 Jul, 8 hari - murni auto-approval) | [7 empty] | SPRINT 2 (24 Jul - 10 Ags, 12 hari - approval flow & email)
| 14/07 | 15/07 | 16/07 | 17/07 | 20/07 | 21/07 | 22/07 | 23/07 | 24/07 | 27/07 | 28/07 | 29/07 | 30/07 | 31/07 | 03/08 | 04/08 | 05/08 | 06/08 | 07/08 | 10/08
SPRINT 1 - Auto Approval PO < USD 500 (8 hari kerja - TIDAK ada task email/SMTP)
Build & Push Program ZPO_AUTO_RELEASE
Setup Mapping ZMAP_TYPE (Threshold & Approver)
Review & Validasi Business Rule Threshold/Release Strategy
Siapkan/Koordinasi Data PO Test <= USD 500
Draft Config Background Job (SM36)
Authorization Disetujui, Aktifkan Job SM36
Testing End-to-End Tier T0 & Bugfix
UAT & Sign-off Tier T0
Siapkan Transport Request (SE09/SE10)
Release ke QAS & Dokumentasi Teknis
Closing / Demo Sprint 1
SPRINT 2 - Approval Flow & Email Notification (12 hari kerja - termasuk setup SMTP dari nol)
Ajukan Request Setup SMTP Relay/SCOT ke Tim Basis
Mulai Finalisasi Requirement Approval Flow (iterasi business)
Follow-up Progress Setup SCOT dgn Tim Basis
Design CONFIG Switch & Kerangka Notifikasi (dormant)
Build Logic Kirim Email (coding, blm butuh SMTP live)
Siapkan & Revisi Template Email (iterasi business/comms)
Bantu Tim Basis Konfigurasi SCOT Node & Test Internal
Gate: Validasi SMTP Relay Berhasil Kirim Email Keluar
Unit Test Pengiriman Email (mode simulasi P_TEST=X)
Finalisasi Daftar Approver & Template
Koordinasi Jadwal Testing E2E dgn Approver
Testing End-to-End Tier T1/T2 (email->approve manual)
Bugfix & Aktifkan Switch NOTIF_ACTIVE
UAT & Sign-off Sprint 2
Transport ke QAS & Dokumentasi Final
Closing/Demo Sprint 2 & Handover
Legend:
Done
In Progress
Planned / Not Started
Tergantung Tim Basis (di luar kendali Budi/Alfa)

## PO Auto Release
Daily Activity - PO Auto Release Automation
SPRINT 1 - Auto Approval PO < USD 500 (8 hari kerja) - MURNI scope auto-release, TIDAK ada task email/SMTP - 14 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-01 Build & push program ZPO_AUTO_RELEASE (v4) - auto-release Tier T0 <USD 500 via BAPI_PO_RELEASE | Program aktif di sandbox-new (TRS) | Program ZPO_AUTO_RELEASE ter-deploy | Done | 100% | 2026-07-14
Budi (ABAP) | SPR1-02 Setup mapping ZMAP_TYPE (THRESHOLD T0/T1/T2 & APPROVER nama+email per EKGRP) | Mapping siap dipakai program | ZMAP_TYPE terisi & tervalidasi | Done | 100% | 2026-07-14
Alfa (Functional) | SPR1-03 Review & validasi business rule threshold USD 500 dan release strategy (FRGGR/FRGSX) | Konfirmasi threshold & release group sesuai proses bisnis | Sign-off business rule Tier T0 | In Progress | 25% | 2026-07-17
SPRINT 1 - Auto Approval PO < USD 500 - 15 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-04 Ajukan request authorization M_EINK_FRG utk user/job batch release ke tim Basis/Security | User job punya otorisasi release PO | Request authorization tercatat | Not Started | 0% | 2026-07-17
Alfa (Functional) | SPR1-05 Siapkan/koordinasi data PO test senilai <= USD 500 di sandbox | Ada PO test valid utk skenario auto-release | PO test tersedia | Not Started | 0% | 2026-07-17
SPRINT 1 - Auto Approval PO < USD 500 - 16 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-06 Draft konfigurasi background job (SM36) - menunggu authorization selesai | Job siap diaktifkan begitu authorization approve | Draft job SM36 | Not Started | 0% | 2026-07-17
Alfa (Functional) | SPR1-07 Lanjut koordinasi data PO test & authorization dengan business | Data & authorization siap sebelum testing | Konfirmasi kesiapan test | Not Started | 0% | 2026-07-17
SPRINT 1 - Auto Approval PO < USD 500 - 17 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-08 Authorization M_EINK_FRG disetujui, aktifkan background job SM36 | Job berjalan otomatis tanpa perlu F8 manual | Job SM36 aktif | Not Started | 0% | 2026-07-17
Alfa (Functional) | SPR1-09 Data PO test <= USD 500 tersedia & siap dipakai testing | PO test valid tersedia | PO test tersedia | Not Started | 0% | 2026-07-17
SPRINT 1 - Auto Approval PO < USD 500 - 20 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi, Alfa | SPR1-10 Jalankan test end-to-end Tier T0, verifikasi BAPI_PO_RELEASE tereksekusi & PO ter-release otomatis | Bukti empiris Tier T0 berhasil release | Hasil test terdokumentasi | Not Started | 0% | 2026-07-20
Budi (ABAP) | SPR1-11 Perbaikan bug (jika ada) dari hasil testing | Program bebas bug blocking | Bugfix (jika ada) | Not Started | 0% | 2026-07-20
SPRINT 1 - Auto Approval PO < USD 500 - 21 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR1-12 UAT bersama user/procurement, sign-off jalur Tier T0 | User setuju hasil auto-release Tier T0 | Berita acara UAT / sign-off | Not Started | 0% | 2026-07-21
Budi (ABAP) | SPR1-13 Siapkan transport request (SE09/SE10), pindah program dari $TMP ke package transportable | Program siap ditransport ke QAS | Transport request dibuat | Not Started | 0% | 2026-07-22
SPRINT 1 - Auto Approval PO < USD 500 - 22 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR1-14 Release transport ke QAS (STMS) & dokumentasi teknis program | Program live di QAS | Dokumentasi teknis (technical spec) | Not Started | 0% | 2026-07-22
SPRINT 1 - Auto Approval PO < USD 500 - 23 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR1-15 Dokumentasi business rule & closing/demo Sprint 1 ke stakeholder (Douglas Tjokro/William) | Sprint 1 resmi ditutup & didemokan | Dokumen closing Sprint 1 | Not Started | 0% | 2026-07-23
SPRINT 2 - Approval Flow & Email Notification (12 hari kerja) - dimulai dari nol, termasuk setup SMTP - 24 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-01 Ajukan request setup SMTP relay/SCOT node ke tim Basis (baru mulai di Sprint 2) | Tim Basis mulai proses setup SCOT | Ticket/request tercatat ke tim Basis | Not Started | 0% | 2026-07-27
Alfa (Functional) | SPR2-02 Mulai finalisasi requirement approval flow (email biasa vs approve-via-link) bersama business | Diskusi scope Sprint 2 dimulai | Draft requirement | Not Started | 0% | 2026-07-27
SPRINT 2 - Approval Flow & Email Notification - 27 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-03 Follow-up progress setup SCOT dengan tim Basis | Progress setup SCOT terpantau | Update status dari tim Basis | Not Started | 0% | 2026-07-29
Budi (ABAP) | SPR2-04 Design CONFIG switch ZMAP_TYPE (TYPE=CONFIG, OPT=NOTIF_ACTIVE) & kerangka FORM notifikasi (dormant) | Switch siap, kode belum aktif | Kerangka kode notifikasi | Not Started | 0% | 2026-07-28
SPRINT 2 - Approval Flow & Email Notification - 28 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-05 Mulai build logic kirim email (FM SO_NEW_DOCUMENT_ATT_SEND_API1) - coding jalan meski SMTP belum live | Fungsi kirim email siap secara kode | Fungsi kirim email (belum teruji) | Not Started | 0% | 2026-07-29
Alfa (Functional) | SPR2-06 Siapkan draft template email (subject/body) | Draft template tersedia | Draft template email | Not Started | 0% | 2026-07-29
SPRINT 2 - Approval Flow & Email Notification - 29 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-07 Bantu tim Basis konfigurasi SCOT node & test kirim email dasar (SBWP) | SCOT node terkonfigurasi & bisa kirim internal test | Node SCOT aktif (uji awal) | Not Started | 0% | 2026-07-30
Alfa (Functional) | SPR2-08 Review & revisi template email bersama business/comms | Template disetujui isi & formatnya | Template revisi | Not Started | 0% | 2026-07-30
SPRINT 2 - Approval Flow & Email Notification - 30 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-09 Gate: Validasi SMTP relay berhasil kirim email keluar dari SAP | Email test berhasil terkirim ke inbox nyata | Bukti pengiriman email berhasil | Not Started | 0% | 2026-07-30
SPRINT 2 - Approval Flow & Email Notification - 31 Juli 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-10 Unit test pengiriman email dari ZPO_AUTO_RELEASE (mode simulasi P_TEST=X), sekarang SMTP sudah live | Email test terkirim sesuai approver mapping | Hasil unit test | Not Started | 0% | 2026-07-31
Alfa (Functional) | SPR2-11 Finalisasi daftar approver (Lisa/Melisa/Fenny) & template final | Mapping approver & template final | Approval isi email final | Not Started | 0% | 2026-07-31
SPRINT 2 - Approval Flow & Email Notification - 3 Agustus 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-12 Koordinasi jadwal testing E2E dengan approver (Lisa/Melisa/Fenny) | Jadwal testing E2E disepakati | Jadwal test E2E | Not Started | 0% | 2026-08-03
SPRINT 2 - Approval Flow & Email Notification - 4 Agustus 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi, Alfa | SPR2-13 Testing end-to-end Tier T1/T2: approver terima email -> approve manual ME29N -> validasi status | Alur notifikasi & approval manual terverifikasi | Hasil test E2E | Not Started | 0% | 2026-08-04
SPRINT 2 - Approval Flow & Email Notification - 5 Agustus 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-14 Perbaikan bug dari hasil testing E2E (jika ada) | Program bebas bug blocking | Bugfix (jika ada) | Not Started | 0% | 2026-08-05
Budi (ABAP) | SPR2-15 Aktifkan switch NOTIF_ACTIVE='X' di sandbox setelah testing OK | Notifikasi email aktif di sandbox | Switch aktif | Not Started | 0% | 2026-08-05
SPRINT 2 - Approval Flow & Email Notification - 6 Agustus 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-16 UAT & sign-off Sprint 2 bersama user/procurement | User setuju alur notifikasi & approval | Berita acara UAT Sprint 2 | Not Started | 0% | 2026-08-06
SPRINT 2 - Approval Flow & Email Notification - 7 Agustus 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi (ABAP) | SPR2-17 Transport Sprint 2 ke QAS & dokumentasi final | Sprint 2 live di QAS | Dokumentasi final | Not Started | 0% | 2026-08-07
SPRINT 2 - Approval Flow & Email Notification - 10 Agustus 2026
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Alfa (Functional) | SPR2-18 Closing/demo Sprint 2 ke stakeholder & handover project | Project selesai & di-handover | Dokumen handover | Not Started | 0% | 2026-08-10

## Catatan Asumsi
Catatan asumsi timeframe (final v4 - scope Sprint 1 & Sprint 2 dipisah bersih sesuai definisi Baginda):
1. Format tabel mengikuti template 'ABAP' & 'Milestones General' pada file (USER) WBS & Daily Activity-COA Automation.xlsx yang di-upload Baginda.
2. KOREKSI dari versi v3: sebelumnya task terkait SMTP/SCOT ditaruh paralel di dalam Sprint 1 supaya lebih cepat - ini SALAH karena mencampur scope Sprint 2 ke fase Sprint 1. Sudah diperbaiki: Sprint 1 sekarang MURNI berisi task auto-approval, tidak ada satupun task email/SMTP.
3. Sprint 1 = 8 hari kerja (14-23 Juli 2026): build program, mapping, validasi business rule, authorization M_EINK_FRG, data PO test, job SM36, testing Tier T0, UAT, transport ke QAS.
4. Sprint 2 = 12 hari kerja (24 Juli - 10 Agustus 2026): SEKARANG dimulai dari nol termasuk request setup SMTP relay/SCOT ke tim Basis (SPR2-01) - bukan lagi jalan paralel di Sprint 1. Konsekuensinya Sprint 2 lebih panjang (12 hari, di ujung atas rentang 8-12 hari yang didiskusikan) dibanding versi sebelumnya (10 hari) karena harus menunggu SMTP relay siap dulu sebelum testing pengiriman email bisa dilakukan.
5. Task-task yang bergantung ke tim Basis (request SMTP, follow-up, bantu konfigurasi, gate validasi) ditandai warna ORANYE di Gantt Chart - semuanya di dalam Sprint 2, bukan Sprint 1.
6. Total timeframe proyek: 20 hari kerja, dari 14 Juli s.d. 10 Agustus 2026.
7. Tim: Budi (ABAP Developer), Alfa (Functional Consultant).
8. Task SPR1-01 dan SPR1-02 ditandai Done 100% karena program ZPO_AUTO_RELEASE v4 dan mapping ZMAP_TYPE sudah selesai dibangun & di-push ke sandbox-new pada percakapan sebelumnya.
9. Estimasi 12 hari Sprint 2 mengasumsikan tim Basis merespons dalam waktu wajar (2-4 hari kerja) untuk setup SCOT. Kalau lebih lambat, Sprint 2 mundur lebih jauh lagi - mohon dikonfirmasi ke tim Basis sesegera mungkin setelah Sprint 2 dimulai.